## MNR HVAC PROJECT(Mumbai)
1 | Code | Store Name | Associate Name | Switch Control Module | fitted | return | HVAC | fitted | return | wireless | fitted | return | Installed person | Data status | Dashboard Creation | Installation Status | Dispatch Date | Remarks after 1 st visit | Remarks after 2nd visit
2 | 4 | Vile Parle | Sachin |  |  |  | 6 | [5 empty] | Vinay |  | Done | Finished | ########
3 | 7 | Crossroads | Sachin | 3 |  |  | 3 |  |  | 1 |  |  | Vinay |  | Done | Finished
4 | 50 | Thakur Mall-Dahisar | Sachin | 3 |  |  | 6 |  |  | 1 |  |  | Vinay |  | Done | Finished | ########
5 | 109 | Shivai-Andheri Kurla Rd | Sachin | 3 |  |  | 4 |  |  | 1 |  |  | Vinay |  | Done | Finished | ########
6 | 227 | Mumbai Anupam Goregaon | Sachin | 3 |  |  | 4 |  |  | 1 |  |  | Vinay |  | Done | Finished | ########
7 | 238 | Mumbai Shalimar | Sachin | 3 |  |  | 4 | [5 empty] | Vinay |  | Done | Finished | ########
8 | 25 | The Hub | Sachin |  |  |  | 4 | [5 empty] | Vinay |  | Pending | Finished | ######## | HVAC not connected
9 | 181 | Mumbai Sai Elegance | Sachin |  |  |  | 6 | [5 empty] | Vinay |  | Done | Finished | ########
10 | 222 | Mumbai Andheri Vaibhav | Sachin |  |  |  | 5 | [5 empty] | Vinay |  | Done | Finished | ########
11 | 305 | Mumbai Bhandup Magnet Mal | Santosh |  |  |  | 2 | [5 empty] | Vinay |  | Done | Finished | ########
12 |  |  |  | 15 |  |  | 44 |  |  | 4
13
PHASE 2
TEAM 2
1 | 284 | Kharghar Pacific Heights | Santosh | 3 |  |  | 5 |  |  | 1
2 | 0145 | Mumbai-Sai Sagar Belapur | Santosh | 3 |  |  | 4 |  |  | 1 | [5 empty] | compltd 22/07
3 | 10 | Thane | Santosh | 3 |  |  | 6 |  |  | 1 | [5 empty] | compltd 27/07
4 | 12 | Kalamboli | Santosh |  |  |  | 9 |  |  | -
5 | 46 | Mumbai Central Ii-Patel | Sachin | 3 | 0 | 3 | 3 | 2 | 1 | 1 | 0 | 1 |  |  |  | compltd 26/07
6 | 153 | Mumbai-Cascade Kandivili | Sachin | 3 |  |  | 2 |  |  | 1
7 | 161 | Mumbai-Vishwamahal Mulund | Santosh | 3 |  |  | 11 |  |  | 1
8 | 220 | Mumbai Unity Hights Malad | Sachin | 3 |  |  | 6 |  |  | 1
9 | 251 | Panvel Balaji Aangan | Santosh | 3 |  |  | 7 |  |  | 1
10 | 344 | Mumbai Thane Ghodbunder | Santosh | 3 |  |  | 5 |  |  | 1
11 | 22 | Borivili | Sachin |  |  |  | 5 |  |  | -
12 | 28 | L.City Thane2 | Santosh |  |  |  | 1 |  |  | -
13 | 56 | Mumbai- Metro Junction | Santosh | 3 |  |  | 5 |  |  | 1
14 | 61 | Mumbai- Om Sai Plaza | Sachin | 3 |  |  | 4 |  |  | 1
15 | 107 | Mumbai-Dahisar Link Rd | Sachin |  |  |  | 5 |  |  | -
16 | 151 | Mumbai-Lodha Boulevard | Santosh |  |  |  | 5 |  |  | -
17 | 163 | Mumbai-Koparkhairane | Santosh |  |  |  | 5 |  |  | - | [5 empty] | compltd 20/07
18 | 171 | Ripples - Navi Mumbai | Santosh |  |  |  | 6 |  |  | - | [5 empty] | compltd 22/07
19 | 193 | Kalyan Shelar Park | Santosh |  |  |  | 6 |  |  | -
20 | 205 | Mumbai Landmark Bhayander | Sachin |  |  |  | 5 |  |  | -
21 | 212 | Mumbai A To Z Vasai | Sachin | 3 |  |  | 5 |  |  | 1
22 | 213 | Mumbai Rabale | Santosh | 3 |  |  | 3 |  |  | 1 | [5 empty] | compltd 22/07
23 | 252 | Walshind Mumbai Nashik Hi | Santosh | 3 |  |  | 5 |  |  | 1
24 | 265 | Mumbai Naigon Maljipada | Sachin | 3 |  |  | 5 |  |  | 1
25 | 319 | Dombivili Gharda Circle | Santosh |  |  |  | 4 |  |  | - | [5 empty] | compltd 26/07
|  |  |  | 45 |  |  | 127 |  |  | 15
PHASE 1
|  |  | TEAM 1 | Switch Control Module | Switch Control Module actul | Return to mum office | HVAC DX Module | HVAC DX Module actul | Return | Wire to wireless | actual fitd | reurn | service engg |  |  |  |  | instaln status 19/07/21 | instaln status 26/07/21
1 | 3 | Vashi Sector-17 | Santosh | 3 |  |  | 5 | 2 | 3 | 1 | [6 empty] | 07.05.21 | partially compltd | 10 to 20%pending fm protch diffnt ac modul reqd
2 | 6 | New Empire | Sachin | 3 |  |  | 2 |  |  | 1 |  |  | anil+suresh |  |  |  | 2021-04-06 | compltd | compltd
3 | 17 | Mulund | Santosh | 3 | 2 | 1 | 4 | 3 | 1 | 1 |  |  | vinay+shinde |  |  |  | 2021-04-06 | Kitchen Ac conction pnding. vip must | Kitchen Ac conction pnding. vip must
4 | 20 | Ghatkopar | Santosh | 3 |  |  | 6 |  |  | 1 | [6 empty] | 2021-04-14
5 | 79 | Mumbai- Mira Bhayandar | Sachin | 3 |  |  | 6 |  |  | 1 | [6 empty] | 2021-04-15
6 | 135 | Mumbai-Cafe Ideal Andheri | Sachin | 3 |  |  | 4 |  |  | 1 | [6 empty] | 2021-04-15
7 | 215 | Mumbai Nts Bandra | Sachin | 3 | 2 | 1 | 9 | 6 | 3 | 1 |  |  | vinay+shinde |  |  |  | 2021-04-16 | compltd | compltd with 2 swtc control ,for remng sw contrl extra cable & vip must for other contrl
8 | 285 | Mumbai Sion Avishkar | Santosh | 3 |  |  | 7 | 4 | 3 | 1 |  |  | suresh |  |  |  | 2021-04-16 | compltd | compltd with 3 swtc control ,for remng sw contrl extra cable & vip must for adding other 2 equpmnt
9 | 294 | Mumbai Vile Parle Nivara | Sachin | 3 |  |  | 9 |  |  | 1 | [6 empty] | 2021-04-14
10 | 299 | Mumbai Artista | Santosh | 3 |  |  | 6 | 5 | 1 | 1 |  |  | anil+suresh |  |  |  | 2021-04-14 | compltd
11 | 1 | Bandra | Sachin |  |  |  | 7 |  |  | - |  |  | vinay+shinde |  |  |  | 2021-05-07 | compltd
12 | 2 | Lokhandwala | Sachin |  |  |  | 5 |  |  | - | [6 empty] | 2021-04-15 |  | compltd 24/07
13 | 15 | Phoenix Mills | Sachin |  |  |  | 4 | 2 | 2 | - |  |  | vinay+shinde |  |  |  | 2021-04-16 | Kitchen Ahu out of store DX module installation not possible.and Loby Ac ON/OFF Connection not possible. (Celing POP )
14 | 18 | Colaba | Sachin |  |  |  | 5 | 2 | 3 | - |  |  | vinay+shinde |  |  |  | 2021-05-07
15 | 70 | Kharghar- Little World | Santosh |  |  |  | 7 | 4 | 3 | - |  |  | anil+suresh |  |  |  | 2021-05-08 | ktchn wirng comlctd vip must
16 | 149 | Mumbai-Star Mall | Sachin |  |  |  | 5 | 3 | 2 | - |  |  | vinay+shinde |  |  |  | 2021-05-05 | compltd
17 | 275 | Mumbai Jogeshwari Jaiswal | Sachin | 3 |  |  | 4 |  |  | 1 | [6 empty] | 2021-04-06
|  |  |  | 33 |  |  | 95 |  |  | 11
|  | stock match rtrn mtrl 26/07 anil |  |  |  | 5 |  |  | 22 |  |  | 1

## DALY COMPLNTS (complain nos on
Sl No | StationID | Store Code | StationName | Region | Status | Nature of Complaint | Equipment Description | Complaint ID | Complaint Date | Log Time | Month | Priority | Feedback | job close Date | job close time | protec Ser engg name | billing(b) or wrnty(w) | If pending more than 15 days reson in shrt(Mcd or Pro)) | Instln rport date | Insln soft cpy sent to prbhu dt | Dt of submisn of hard cpy to a/c | final closer date our end (only aftr rport hrd copy to a/c) | Inv generated dt | Pod to mcd | Soft copy to mcd dt | Payment rcpt dt | Sl No | StationID | Store Code | StationName
0 | 7997993017 | BA95 | Lido Mall | South | Closed | Main enegy meter problem | EMS | NA | 22/08/2020 | 11:00 | Aug | NA | CT colis Replaced | 2020-09-15
1 | 2019000007 | 0334 | Trillium Mall Nagpur | West | Closed | EMS Not working | EMS | M2579 | 2020-06-16 | 12:32 | Jun | NA | Sim card Replaced | 2020-09-10
2 | 7997993048 | 0242 | Pune Sonali | West | Closed | EEMS Relay box connectivity issue | EMS | M5673 | 2020-08-29 | 15:52 | Aug | NA | Mother Board issue cleard | 2020-09-22
3 | 8886618890 | 0270 | Pune Royal Dora | West | Closed | EEMS Relay box connectivity issue | EMS | M5674 | 2020-08-29 | 15:52 | Aug | NA | Mother Board Changed now working | 2020-10-13
4 | 9666093127 | 0011 | Pune-Jm Road | West | Closed | EEMS Relay box connectivity issue | EMS | M5738 | 2020-08-30 | 21:00 | Aug | NA | Loose conncection in relay box | 2020-06-09
5 | 7658953300 | 0109 | Shivai , A K Road | West | Closed | Economiser Run time Meter not working | EMS | M5753 | 2020-08-31 | 14:10 | Aug | NA | Munter Module Issue sended to factory | 2020-11-25
6 | 8886616135 | 0006 | New Empire | West | Closed | EEMS reading not shown | EMS | M5754 | 2020-08-31 | 14:10 | Aug | NA | Due to short circuit Readings Not showing | 2020-08-31
7 | 8886616134 | 0015 | Phoenix Mills | West | Closed | EEMS reading not shown | EMS | M5755 | 2020-08-31 | 14:10 | Aug | NA | Sim card Changed new one | 2020-11-09
8 | 2019000121 | 0343 | Nirman Heights | West | Closed | Main Meter CT Need to be replace | EMS | M5759 | 2020-08-31 | 15:00 | Aug | NA | No need | --
9 | 9666091715 | 0050 | Thakur Mall- Dahisar | West | Closed | Main Meter CT Need to be replace | EMS | M5760 | 2020-08-31 | 15:00 | Aug | NA | No need | --
10 | 9666091638 | 0135 | Café Ideal - Andheri | West | Closed | Main Meter not working | EMS | M5761 | 2020-08-31 | 15:00 | Aug | NA | Communication Cable Removed | 2020-06-10
11 | 7658943300 | 0217 | Aurangabad | West | Closed | Munter Run Timer hrs not working | EMS | M5762 | 2020-08-31 | 15:00 | Aug | NA | Cable Changed issue Cleared | 2020-11-28
12 | 9666092371 | 0087 | Bpcl Khedshivapur - Rom | West | Closed | EMS not working properly | EMS | M5896 | 2020-03-09 | 21:42 | Sep | NA | Mother board Replaced | 2020-09-30
13 | 2017000067 | 0285 | Mumbai Sion Avishkar | West | Closed | HVAC Reading not shown in EEMS | EMS | M5930 | 2020-04-09 | 17:10 | Sep | NA | No Load On Hvac Meters | 2020-10-13
14 | 9666093184 | 0043 | P C M C | West | Closed | Main enegy meter problem | EMS | M4784 | 2020-08-28 | 14:10 | Aug | NA | Energy meter changed | 2020-09-29
15 | 9951950071 | 0254 | LB Nagar | South | Closed | EMS Room Temp sensor not working | EMS | M6081 | 2020-09-09 | 12:37 | Sep | NA | New Sensor replaced | 2020-09-15
16 | 9666093054 | 0064 | Sacred World | West | Closed | Signal Very Low | EMS | M6164 | 2020-11-09 | 9:14 | Sep | NA | New Sim card Replaced | 2020-09-29
17 | 9951945925 | 0265 | Mumbai Naigon Maljipada | West | Closed | EMS not working properly | EMS | M6589 | 2020-09-22 | 19:12 | Sep | NA | Signal issue in site | 2020-09-28
18 | 2018000013 | 0222 | Vaibhav Andheri | West | Closed | Energy Meter issue | EMS | M6545 | 2020-09-26 | 9:30 | Sep | NA | Enetgy Meter Replaced from Nts Bandra | 2020-01-10
19 | 2018000107 | 0336 | Korum Mall west | West | Closed | Ems Units Not Showing | EMS | M6727 | 2020-09-28 | 16:30 | Sep | NA | Sim Card need to Change | 2020-12-28
20 | 2019000120 | 0363 | Blue Ridge Hinjewadi | West | Closed | Munter run timer data not coming in EEMS | EMS | M7145 | 2020-08-10 | 13:45 | Oct | NA | communication cable changed | 2020-09-10
21 | 9666093062 | 0065 | Kolhapur Highway | West | Closed | Munter run timer data not coming in EEMS | EMS | M7159 | 2020-08-10 | 19:00 | Oct | NA | Fuse Changed | 2020-10-17
22 | 9951082951 | G262 | MCDonaldMall Goa | West | Closed | 10 Channel Switch control are not working | EMS | M7298 | 2020-08-28 | 14:10 | Oct | NA | Mother board version Need to change | 2020-11-17
23 | 8886618894 | 0251 | Panvel | West | Closed | Main panel reading not coming | EMS | M7398 | 2020-10-14 | 14:18 PM | Oct | NA | Communiction Checked Only Two meters in store. | 2020-10-27
24 | 2017000056 | 0067 | Channapatna | South | Closed | EMS is not working | EMS | M7471 | 2020-10-15 | 18:24 PM | Oct | NA | Signal issue in site | 2020-10-16
25 | 2018000079 | 0146 | Fun Republic Mall | South | Closed | Gas meter is not working | EMS | M7485 | 2020-10-16 | 11:31 | Oct | NA | Out off warrenty | 2020-11-11
26 | 9666093184 | 0043 | P C M C | West | Closed | EEMS reading is not correct | EMS | M7811 | 2020-10-25 | 9:27 | Oct | NA | Changes done in server | 2020-12-18
27 | 2017000063 | 0286 | Nazarathpet | South | Closed | Lobby EMS sensor is not wokring | EMS | M7916 | 2020-10-28 | 13:08 PM | Oct | NA | Replaced New Lobby Sensor | 2020-10-31
28 | 7658945550 | 0210 | CenturionMall | West | Closed | EMS not working, | EMS | M8257 | 2020-05-11 | 18:38 PM | Nov | NA | Sim card Replaced | 2020-11-13
29 | 2019000120 | 0363 | Blue Ridge Hinjewadi | West | Closed | Munter Run Time not showing in EMS. | EMS | M8375 | 2020-09-11 | 12:24 | Nov | NA | Names interchanged | 2020-10-11
30 | 7658945550 | 0039 | Brigade | South | Closed | Diesel reading not showing | EMS | M8416 | 2020-10-11 | 13:32 PM | Nov | NA | Fuel Sensor Not Working Need to change Wire to wireless | 2020-12-11
31 | 2017000063 | 0286 | Nazarathpet | South | Closed | potential controller not working - Reg | EMS | M8483 | 2020-12-11 | 12:08 | Nov | NA | Communication Cable Given to Controller ON/Off Checked | 2020-12-11
32 | 2018000102 | 0331 | Pondy Bazaar | South | Closed | potential controller not working - Reg | EMS | M8484 | 2020-12-11 | 12:08 | Nov | NA | Communication Cable Given to Controller ON/Off Checked | 2020-12-11
33 | 2017000054 | 0209 | J.P. Nagar | South | Closed | Cold room data need to added in kitchen & Munter data | EMS | M9040 | 2020-11-27 | 14:59 PM | Nov | NA | Internally Conncection Changed | 2020-12-06
34 | 2017000058 | 0100 | Baseshwara Nagar | South | Closed | EMS installation issue & HVAC data not coming . | EMS | M9039 | 2020-11-27 | 14:59 PM | Nov | NA | Material Requried Ct Coils 100/5 cable 6 core,4 core | 2020-06-12
35 | 9666091356 | 0039 | Brigade | South | Closed | HVAC data not coming & Munter data need to add in HVAC . | EMS | M9038 | 2020-11-27 | 14:59 PM | Nov | NA | Mother board Changed munter added in hvac meter | 2021-02-11
36 | 9848350615 | 0139 | KamanahalliI | South | Closed | HVAC data not coming & Munter data need to add in HVAC | EMS | M9037 | 2020-11-27 | 14:59 PM | Nov | NA | Connections given to hvac Meter readings are showing | 2020-03-12
37 | 7997993037 | 0206 | Gaganpahad | South | Closed | Kitchen Energy meter not showing proper consumption @Gaganpahad | EMS | M9067 | 2020-11-28 | 12:10: PM | Nov | NA | CT Ratioo Problem in meter no issue from our End | 2020-11-28
38 | 2017000063 | 286 | Nazarathpet | South | Closed | Need new terminal box | EMS | M9152 | 2020-11-30 | 20:30 PM | Nov | NA | Installation Completed | 2020-12-02
39 | 2017000013 | 188 | ChandKheda | West | Closed | Whole system not working | EMS | M9221 | 2020-02-12 | 20:37 PM | DEC | NA | CT Coils Replaced for all meters | NIL
40 | 9666098041 | 192 | SamaSavali Vadodara | West | Closed | System Not working + HVAC and Munter data not capturing | EMS | M9220 | 2020-02-12 | 20:37 PM | DEC | NA | Mother board Replaced | 2021-01-10
41 | 9133382109 | 278 | DeepakMall Surat | West | Closed | System Data not coming + Munter and HVAC data not showing | EMS | M9219 | 2020-02-12 | 20:37 PM | DEC | NA | Two Energy meter installed Cleard | 2021-01-23
42 | 2017000064 | 312 | K10 Atlantis Vadodara | West | Closed | EB reading is in correct | EMS | M9218 | 2020-02-12 | 20:37 PM | DEC | NA | Need to visit | 2021-02-05
43 | 7729986542 | 243 | Baruch | West | Closed | KITCHEN MUNTER DATA NOT SHOWING + HVAC DATA SHOWING HIGH + RELAY COMUNICATION NOT HAPPENING | EMS | M9217 | 2020-02-12 | 20:37 PM | DEC | NA | CT Ratio Changed | 2020-12-07
44 | 8498059360 | 168 | Millionaire Surat | West | Closed | MIS Consumption is high | EMS | M9216 | 2020-02-12 | 20:37 PM | DEC | NA | Main meter readings are ok please cross check what all meters connected to Hvac and Kitchen meter | 2020-12-03
45 | 2018000037 | 74 | ValentineMall Surat | West | Closed | EB reading is in correct | EMS | M9215 | 2020-02-12 | 20:37 PM | DEC | NA | Hvac and kitchen meter not installed | 2020-12-03
46 | 2017000026 | 38 | TNW Vadodara | West | Closed | EB reading is in correct | EMS | M9214 | 2020-02-12 | 20:37 PM | DEC | NA | CT Ratio Entered in Meter worng | 2020-12-05
47 | 9666092148 | 120 | PAUD Road | West | Closed | Ems diesel meter not showing sensor problem | EMS | M9297 | 2020-05-12 | 13:22 PM | DEC | NA | Communication cable damaged | 2020-12-08
48 | 2017000063 | 286 | Nazarathpet | South | Closed | temperature and humidity sensors required | EMS | M9389 | 2020-07-12 | 17:40 PM | DEC | NA | Installation Completed | 2020-12-11
49 | 2018000102 | 331 | Pondy Bazaar | South | Closed | temperature and humidity sensors required | EMS | M9390 | 2020-07-12 | 17:40 PM | DEC | NA | Installation Completed | 2020-12-11
50 | 2018000089 | 295 | Nalasopara | West | Closed | EEMS data transfer not happening | EMS | M9575 | 2020-12-13 | 18:03 PM | DEC | NA | Mother Board Changed now working | 2020-12-18
51 | 2018000004 | 307 | GrandCentral Kakkanad | South | Closed | kitchen Kwh meter not working | EMS | M9682 | 2020-12-16 | 21:12 PM | DEC | NA | Communication Problem | 2021-01-07
52 | 9666089326 | 159 | OMR | South | Closed | kitchen Kwh meter not working | EMS | M9681 | 2020-12-16 | 21:12 PM | DEC | NA | Communication Cable interchaged | 2020-12-18
53 | 2018000102 | 331 | T. Nagar, Pondy Bazaar | South | Closed | kitchen Kwh meter not working | EMS | M9679 | 2020-12-16 | 21:12 PM | DEC | NA | Meter changed | 2020-12-31
54 | 9666089015 | 177 | Ashok Nagar | South | Closed | kitchen Kwh meter not working | EMS | M9678 | 2020-12-16 | 21:12 PM | DEC | NA | Mother Board Changed now working | 2020-12-29
55 | 7997993037 | 206 | Gaganpahad | South | Closed | Sim port is not working | EMS | M9696 | 2020-12-17 | 12:34 | DEC | NA | GSM Modem issue, Modem changed issue cleared. | 2020-12-17
56 | 7729986532 | 76 | Bull Temple Gandhi bazar | South | Closed | HVAC data not coming & Munter need to add in HVAC & Kitchen data showing less & Cold room need to add in kitchen data . | EMS | M9818 | 2020-12-19 | 18:10 PM | DEC | NA | Internally Conncection Changed | 2020-12-26
57 | 7997993013 | 81 | Kempfort | South | Closed | Kitchen unit showing very less , cold room need to add in Kitchen data & Munter need to add in HVAC. | EMS | M9819 | 2020-12-19 | 18:10 PM | DEC | NA | From Our end Hvac and Machine running hours add In hvac meter | 2020-12-25
58 | 9666090861 | 85 | BEL Road | South | Closed | Kitchen unit showing very less & cold room need to connect in Kitchen data . | EMS | M9830 | 2020-12-19 | 18:10 PM | DEC | NA | No issue from our end | 2021-03-05
59 | 9133382081 | 103 | HSR Layout | South | Closed | HVAC data not coming & Cold room need to add in kitchen data | EMS | M9820 | 2020-12-19 | 18:10 PM | DEC | NA | all Hvac are connected to hvac meter | 2021-01-05
60 | 2017000008 | 204 | Sahakar Nagar | South | Closed | Kitchen & HVAC data less coming , Munter need to add in HVAC & Cold room need to add in kitchen data. | EMS | M9821 | 2020-12-19 | 18:10 PM | DEC | NA | Ct Coils Change for Kitchen meter and Hvac Meter | 2021-01-24
61 | 8886618893 | 247 | HighywayStar Kolar | South | Closed | Main EB data coming less & HVAC data not coming & Munter need to add in HVAC data | EMS | M9822 | 2020-12-19 | 18:10 PM | DEC | NA | CT Coils Replaced for Main Meter | 2021-03-10
62 | 9951947657 | 257 | Ascendas | South | Closed | HVAC data not coming & Kitchen data showing less | EMS | M9823 | 2020-12-19 | 18:10 PM | DEC | NA | Internally Connection cross Checked our end no issue | 2021-02-05
63 | 2018000052 | 314 | Soul Space | South | Closed | Kitchen data showing less & HVAC data not coming | EMS | M9824 | 2020-12-19 | 18:10 PM | DEC | NA | Energy Meter need to installed with Ct coils pending | 2020-12-29
64 | 2018000097 | 328 | Akshay Nagar | South | Closed | Kitchen & HVAC data less coming & Munter need to add in HVAC data. | EMS | M9825 | 2020-12-19 | 18:10 PM | DEC | NA | kitchen Energ meter CT installation Completed | 2021-02-04
65 | 9666101791 | 66 | Kasturba Road | South | Closed | HVAC data not coming, Munter need to add in HVAC & Cold room add in Kitchen | EMS | M9826 | 2020-12-19 | 18:10 PM | DEC | NA | Internally Conncection Changed | 2021-01-10
66 | 9666098419 | 94 | CMH-2 | South | Closed | HVAC data not coming properly, Munter need to add in HVAC data & Cold room need to add in Kitchen data | EMS | M9827 | 2020-12-19 | 18:10 PM | DEC | NA | Internally Conncection Changed | 2021-01-10
67 | 2017000055 | 117 | Minakshi Mall | South | Closed | HVAC data not coming & Kitchen data showing less | EMS | M9828 | 2020-12-19 | 18:10 PM | DEC | NA | No issue from our end | 2021-03-04
68 | 7658937700 | 104 | Jayanagar | South | Closed | HVAC data not coming & Cold room need to add in kitchen data | EMS | M10050 | 2020-12-15 | 16:00 PM | DEC | NA | Internally Conncection Changed | 2020-12-24
69 | 2018000005 | 155 | Vijaya Nagara | South | Closed | Main EB data coming very less . | EMS | M10049 | 2020-12-16 | 14:00 PM | DEC | NA | Internally Conncection Changed | 2020-12-24
70 | 7997993016 | 88 | JP CentralMall | South | Closed | HVAC data not coming & Cold room need to add in kitchen data | EMS | M10047 | 2020-12-22 | 13:00 PM | DEC | NA | Internally Conncection Changed | 2020-12-24
71 | 9133382100 | 89 | Arch Mall | South | Closed | HVAC data not coming & Cold room need to add in kitchen data | EMS | M10048 | 2020-12-21 | 13:00 PM | DEC | NA | New energy meter installed and internally connection changed | 2021-01-22
72 | 9666087360 | 154 | Kilpauk | South | Closed | EMS Reading is not showing by system. | EMS | M9960 | 2020-12-22 | 12:39 | DEC | NA | Voltage Issue in Phases | 2020-12-29
73 | 2018000050 | 323 | Providence mall-Puducheery | South | Closed | EMS Reading is not showing by system. | EMS | M9961 | 2020-12-22 | 12:39 | DEC | NA | C T Coils Issue Cleard | 2020-12-29
74 | 9666087824 | 83 | Anna Nagar | South | Closed | TWO Main EB meter are not working | EMS | M10035 | 2020-12-23 | 19:34 PM | DEC | NA | C T Coils Issue Cleard | 2020-12-31
75 | 2019000011 | 338 | BNR SV Mall Tirupati | South | Closed | HVAC units showing very low on EMS | EMS | M10079 | 2020-12-24 | 10:01 | DEC | NA | System data checked | 2020-12-31
76 | 2017000001 | 114 | Shoolagiri | South | Closed | HVAC units not showing on EMS | EMS | M10078 | 2020-12-24 | 10:01 | DEC | NA | Hvac Ct coils need to change | 2021-02-02
77 | 7658951114 | 27 | Marigold | West | Closed | Health check up requirement for all equipement taking care by wang Protech | EMS | M10097 | 2020-12-25 | 12:30 | DEC | NA | Installation Completed
78 | 9133382098 | 69 | Gmr Airport - Hyderabad | South | Closed | Kitchen meter not connected to Complete Kitchen Equipment. | EMS | M10231 | 2020-12-28 | 16:42 PM | DEC | NA | Installation Completed | 2021-01-07
79 | 7997993036 | 191 | Mehdipatnam | South | Closed | HVAC meter not connected to Complete HVAC equipment. | EMS | M10230 | 2020-12-28 | 16:42 PM | DEC | NA | CT colis Replaced | 2021-01-05
80 | 2018000009 | 91 | In Orbit ,Hyd | South | Closed | HVAC meter not available | EMS | M10229 | 2020-12-28 | 16:42 PM | DEC | NA | Hvac meter installed and communication give to console | 2021-03-02
81 | 2018000007 | 42 | Prasad Imax | South | Closed | HVAC meter not available | EMS | M10228 | 2020-12-28 | 16:42 PM | DEC | NA | Meter installed New hvac meter | 2021-01-09
82 | 9666095106 | 84 | Empress City Center | West | Closed | EEMS data is incorrect | EMS | M10305 | 2020-12-29 | 17:40 PM | DEC | NA | CT ratio wrong in all energy meters | 2021-01-22
83 | 2017000065 | 313 | Indoor - T I 2 | West | Closed | All equipment health check up need to be carry out | EMS | M10295 | 2020-12-29 | 17:40 PM | DEC | NA | Need to visit
84 | 7729986542 | 243 | Baruch | West | Closed | EEMS relay box communication issue and data showing incorrect. | EMS | M10435 | 2021-01-03 | 14:59 PM | DEC | NA | Mother Board Changed now working | 2021-01-07
85 | 9133382106 | 215 | MUM-0215-NTS Bandra | West | Closed | Ems Units Showing wrong | EMS | M10529 | 2021-01-05 | 18:40 PM | Jan | NA | Ct Coils issue changed | 2021-01-18
86 | 2018000101 | 330 | Travancore (KRL) | South | Closed | EMS meter is not working | EMS | M10503 | 2021-01-05 | 10:31 | Jan | NA | Hvac Meter setting problem | 2021-01-30
87 | 9951945673 | 255 | HYD-0255-Nellore | South | Closed | EMS meter is not working | EMS | M10502 | 2021-01-05 | 10:31 | Jan | NA | Internally Connection changed | 2021-01-28
88 | 7729986540 | 60 | HYD-0060-ASRaoNagar | South | Closed | EMS not working in kitchen area. | EMS | M10672 | 2021-01-10 | 12:35 | Jan | NA | Communication Problem issue cleared | 2021-01-11
89 | 2019000096 | 356 | Khalapur Oceans and food Plaza | West | Closed | GAS and DG unit not showing. | EMS | M10896 | 2021-01-15 | 20:12 PM | Jan | NA | Need to visit | 2021-02-01
90 | 2017000004 | 282 | Bengaluru Virtous Mall | South | Closed | EMS main meter data not coming correctly. | EMS | M10895 | 2021-01-15 | 20:09 PM | Jan | NA | Main Meter Ct Coils Replaced cleard | 2021-01-30
91 | 9666095106 | 84 | Empress City Centre,Vapi | West | Closed | Huge variation in Mis units | EMS | M10891 | 2021-01-15 | 18:35 PM | Jan | NA | CT ratio wrong in all energy meters | 2021-01-22
92 | 2018000110 | 317 | Bopal Ahmedabad | West | Closed | Data not showing | EMS | M10890 | 2021-01-15 | 18:34 PM | Jan | NA | Signal issue in site | 2021-01-19
93 | 9666098041 | 192 | Sama Savali Baroda | West | Closed | Kitchen Data not coming | EMS | M10889 | 2021-01-15 | 18:33 PM | Jan | NA | kitchen Energ meter installed | 2021-01-28
94 | 2017000017 | 26 | Ahmbd Maninagar | West | Closed | Required HVAC and Kitchen Meter | EMS | M10888 | 2021-01-15 | 18:32 PM | Jan | NA | Material Sent For Hvac and kitchen meter | 2021-02-02
95 | 2018000037 | 74 | Valentine Mall, Surat | West | Closed | HVAC Data is not coming | EMS | M10887 | 2021-01-15 | 18:31 PM | Jan | NA | Main meter Ct Coils installed and hvac Meter installed | 2021-01-22
96 | 7658940002 | 199 | Kalawad Road - Rajkot | West | Closed | Meter installation | EMS | M10886 | 2021-01-15 | 18:30 PM | Jan | NA | Need to visit | NIL
97 | 2017000025 | 223 | Nadiad - Gujarat | West | Closed | EB Data is low in reading | EMS | M10885 | 2021-01-15 | 18:29 PM | Jan | NA | Two Mains in site | 2021-02-05
98 | 2017000010 | 108 | Safal Pegasus | West | Closed | EMS data not coming | EMS | M10884 | 2021-01-15 | 18:27 PM | Jan | NA | Signal issue in site | 2021-01-21
99 | 2019000114 | 366 | Prabhadevi Kohinoor | West | Closed | EMS Reading is not proper.. | EMS | M10883 | 2021-01-15 | 18:26 PM | Jan | NA | Main meter CT Coil Issue | 2021-01-19
100 | 2019000129 | 361 | Mumbai Borivali Sanskruti Splendor | West | Closed | EMS Reading is not proper.. | EMS | M10882 | 2021-01-15 | 18:25 PM | Jan | NA | Main meter CT Coil Issue | 2021-01-19
101 | 2019000082 | 357 | Saifee Cluster | West | Closed | EMS Reading is not proper.. | EMS | M10881 | 2021-01-15 | 18:24 PM | Jan | NA | Main meter CT Coil Issue | 2021-01-19
102 | 2019000049 | 345 | Khetan Bhavan | West | Closed | EMS Reading is not proper.. | EMS | M10880 | 2021-01-15 | 18:23 PM | Jan | NA | Main meter CT Coil Issue | 2021-01-19
103 | 2019000121 | 343 | Nirman Heights | West | Closed | EMS Reading is not proper.. | EMS | M10879 | 2021-01-15 | 18:22 PM | Jan | NA | Main meter CT Coil Issue | 2021-01-19
104 | 2020000001 | 374 | Cochin ABAD Nucleus Mall | South | Closed | EMS is not working | EMS | M10878 | 2021-01-15 | 18:21 PM | Jan | NA | Signal issue in site | 2021-01-19
105 | 9666092148 | 120 | PAUD Road | West | Closed | Ems HVAC meter not showing | EMS | M10929 | 2021-01-16 | 19:19 PM | Jan | NA | Hvac meter installed and communication give to console | 2021-01-19
106 | 9666092275 | 54 | HinjeWadi | West | Closed | Second HVAC meter not showing in system . | EMS | M10928 | 2021-01-16 | 18:18 PM | Jan | NA | Hvac meter installed and communication give to console | 2021-01-19
107 | 7997993011 | 140 | Signature Mall | South | Closed | EMS data Not Pick Properly at on line systems. | EMS | M10968 | 2021-01-17 | 19:56 PM | Jan | NA | Signal issue in site | 2021-01-19
108 | 2017000011 | 176 | Science City | West | Closed | EMS reading issue | EMS | M10967 | 2021-01-17 | 17:57 PM | Jan | NA | Two Mains in site | 2021-02-05
109 | 9666095260 | 203 | Gujnan Vapi | West | Closed | EMS reading issue | EMS | M11197 | 2021-01-22 | 21:04 PM | Jan | NA | internally Hvac all mcb not passed to through hvac meter | 2021-01-22
110 | 9951953598 | 261 | Kamaraj Surat | West | Closed | EMS reading issue | EMS | M11198 | 2021-01-22 | 21:04 PM | Jan | NA | Cross checked communication and ratio cleared | 2021-01-23
111 | 9848350615 | 139 | KamanahalliI | South | Closed | Diesel consumption is not showing | EMS | M11725 | 2021-02-04 | 20:20 PM | Feb | NA | Cable Changed issue Cleared | 2021-02-27
112 | 9133382082 | 180 | Jnc Koramangala | South | Closed | Gas Reading not coming in EMS . | EMS | M11919 | 2021-02-09 | 19:48 PM | Feb | NA | Communication Cable damaged. | 2021-02-20
113 | 2017000066 | 306 | Manipal | South | Closed | EMS Kitchen and HVAC data not coming | EMS | M11504 | 2021-01-30 | 13:40 PM | Jan | NA | No issue from our end Connection need to interchange from store end | 2021-08-11 | 17:00PM | Madhu
114 | 2018000015 | 225 | ForumFizaMall Mangalore | South | Closed | EMS data miscellaneous units showing high need | EMS | M11963 | 2021-02-11 | 11:40 | Feb | NA | New enery meter installed | 2021-07-08 | 18:00PM | Madhu | Billing
115 | 9666098645 | 184 | DownTown Park | South | Closed | EMS data miscellaneous units showing high need to resolve . | EMS | M11964 | 2021-02-11 | 11:40 | Feb | NA | CT Coils Installed for HVAC | 2021-02-19
116 | 9951948430 | 250 | MagnetMall Raipur | West | Closed | EEMS is not working | EMS | M12075 | 2021-02-13 | 18:05 PM | Feb | NA | Need to visit | NIL
117 | 9666089162 | 90 | Grand Arcade | South | Closed | kwh meter installation work | EMS | M12244 | 2021-02-16 | 13:30 PM | Feb | NA | Informed to Ranesh Sir to visit. | 22-06-2021 |  | Chennai Rangesh Sir |  |  | 2021-06-22 | soft copy by whatsapp to anil | 27/06/2021 | yes
118 | 2019000020 | 342 | Igatpur | West | Closed | EEMS is not working | EMS | M12724 | 2021-02-25 | 13:58 PM | Feb | NA | Cable and Mother board changed | 2021-03-06
119 | 2019000083 | 332 | Hyderabad - Miyapur - GSM Mall, | South | Closed | EMS main meter not working | EMS | M12971 | 2021-03-03 | 15:25 PM | Mar | NA | Main meter Ct Coils installed | 2021-03-04
120 | 8886616137 | 1 | Bandra | West | Closed | EMS System Not Working | EMS | 232777450 | 2020-04-14 | 14:20 PM | April | NA | Signal problem location changed. | 2021-04-15
121 | 7658953300 | 109 | Shivai , A K Road | West | Closed | EMS System Not Working | EMS | 232779976 | 2020-04-14 | 14:20 PM | April | NA | Mother Board issue cleard | 2021-04-20
122 | 2018000011 | 149 | Star Mall | West | Closed | EMS System Not Working | EMS | 232777804 | 2020-04-14 | 14:20 PM | April | NA | Sim card Not working replaced new sim Card | 2021-04-22
123 | 9666089162 | 316 | VR Mall Koyembedu | South | Closed | Ems Reading Not Showing | EMS | 246788187 | 2021-05-05 | 13:00PM | May | NA | Informed to Ranesh Sir to visit. | 23-06-2021 |  | Chennai Rangesh Sir |  |  | 2021-06-23 | soft copy by whatsapp to anil | 27/06/2021 | yes
124 | 7997993042 | 233 | Hubbli | South | Closed | Gas Reading not Showing in EMS | EMS | 247576145 | 2021-05-06 | 7:00 | May | NA | Gas flow meter Mother board servicing done distached today. | 27-06-2021 |  | ---
125 | 7997993035 | 138 | Hitech city | South | Closed | Gas Reading not getting proper | EMS | 247999143 | 2021-05-07 | 10:00 | May | NA | kitchen meter ct coil ratio changed and gasmeter calibration done | closed (31/8/21) |  | Anil | no bill | FSR Recieved
126 | 7997993037 | 206 | Gaganpahad | South | Closed | Gas Reading not getting proper | EMS | 247997195 | 2021-05-07 | 10:00 | May | NA | gas flow meter calibration done | closed |  | Anil | no bill | no response
127 | 7997993039 | 240 | AppajiNagar | South | Closed | Gas Reading not getting proper | EMS | 248003245 | 2021-05-07 | 10:00 | May | NA | 01/07,prabhu+ravi had a concall with prasd karri | closed |  | Bala Koteshwar | no bill | no response
128 | 2018000023 | 315 | Kadugodi | South | Closed | Switch Controller not working | EMS | 265300337 | 2021-05-31 | 14:30 PM | May | NA | Madhu visting tomorrow | 24-06-2021 |  | Madhu
129 | 2018000004 | 307 | GrandCentral Kakkanad | South | Closed | Ems reading not getting picked | EMS | 257782011 | 2021-05-23 | 21:00 PM | May | NA | GSM Anteena Changed | 2021-06-01
130 | 7997993038 | 226 | Uppal | South | Closed | Ems Not working | EMS | 260046148 | 2021-05-24 | 10:00 | May | NA | GSM Modem & GSM Anteena Changed | 2021-05-29
131 | 9666092915 | 208 | Loni Kalbhor | West | Closed | Gas Flow meter not working | EMS | 258916646 | 2021-05-22 | 10.00 PM | May | NA | New Gas flow meter dispatched | 21-06-2021 |  |  | b |  | flow mtr fixed by mcd
132 | 9951950071 | 254 | LBNagar | South | Closed | Vats are getting off Continusely | EMS | 266630610 | 2021-06-02 | 9:43 | June | NA | GSM Anteena Changed | 2021-06-08
133 | 9666093184 | 43 | P C M C | West | Closed | Ems control Gas flow meter not working | EMS | 255548741 | 2021-06-05 | 21:30 | June | NA | New Gas flow meter dispatched | 30-06-2021 |  | Nitin | b |  | 30/06/21 | 30/06/21
135 | 9951083071 | 246 | SujanaForum Mall | South | Closed | Ems Not working | EMS | 273370970 | 2021-06-13 | 10:00 | June | NA | Signal problem | 2021-06-14
136 | 7997993024 | 2 | Lokhandwala Complex | West | Closed | Ems Not working | EMS | 274087972 | 2021-06-14 | 17:01 | June | NA | Sim Card issue | 2021-06-14
137 | 9666089671 | 158 | BroadwayAve Vasai | West | Closed | EMS Not working and Gas Meter not working | EMS | 274088844 | 2021-06-14 | 17:01 | June | NA | Signal issue in site | 2021-06-17
134 | 2018000088 | 326 | Pune-Kharadi | West | Closed | Gas Flow meter not working | EMS | 268984184 | 2021-06-05 | 8.00 PM | June | NA | New Gas flow meter dispatched | Closed |  |  | b
139 | --- | 153 | Cascade- Mumbai | West | Closed | New EMS installation | EMS | 274272229 | 2021-06-14 | 17:01 | June | NA | qte sent 06/07 | closed |  | Vinay | no bill | sachin sir mail21/07
140 | 2018000025 | 319 | Dombivili East | West | open | Gas meter not working | EMS | 273597534 | 2021-06-14 | 0:00 | June | NA | Quote need to send for flow meter |  |  | Vinay
141 | 9666092634 | 129 | Lonawala Square | West | Closed | GSM Antenaa reqired | EMS | 275387670 | 2021-06-16 | 16:00 | June | NA | Gsm Anteena dispatched | 2021-06-21 |  | ---
142 | 2018000024 | 213 | Rabale Navi Mumbai | West | open | Diesel generatore sensor need to connect | EMS | 278041900 | 2021-06-20 | 14:15 PM | June | NA | Quote sent waiting for approvel |  |  | Vinay
144 | 9951947837 | 253 | Nasik2 | West | Closed | Diesel generatore readings not showing | EMS | 281232140 | 2021-06-25 | 13:15 PM | June | NA | Power supply board dispatched DC pending |  |  | Nitin | Billing
146 | 2018000003 | 93 | BGL-0093-ForumMall Whitefield | South | Closed | Ems Contol Relay is not on | EMS | 282073207 | 2021-06-26 | 13:15 PM | June | NA | Pairing Done working | 2021-07-15 | 17:00 PM | Madhu
148 | 9666089015 | 177 | Ashok Nagar | South | Closed | Gas meter not working | EMS | 284549643 | 2021-06-28 | 17:00 PM | June | NA | Gas Flow meter not working Mtrl qte sent on 20/7 | 30-07-21 | 18:00 PM | Rangesh Sir | Billing
150 | 2018000079 | 146 | Fun Republic Mall-Coimbatore | South | Closed | Gas meter not working | EMS | 284707487 | 2021-06-25 | 19:00 PM | June | NA | Gas flow meter servicing Done waiting for po mtrl qte sent 20/7 | 2021-04-08 | 18:00 Pm | Rangesh Sir | b
152 | 9676110586 | 105 | Himayathnagar | West | open | DG fuel data not showing | EMS | 284427298 | 2021-06-29 | 13:37 PM | June | NA | Dg Module not working sent to factory waiting for approvel |  |  | Anil
154 | 2018000074 | 151 | Lodha Boulevard Thane | West | Closed | Ems Meter need to installation for walk in freezer | EMS | 284736741 | 2021-06-30 | 10:30 | June | NA | Installation Completed | 2021-07-02 | 14:00PM | Vinay
156 | 2018000040 | 161 | MUM-0161-Vishwamahal Mulund | West | Closed | Kitchen Ac and Freezer readings not showing in Ems | EMS | 277983308 | 2021-06-30 | 10:30 | June | NA | Communication cable Loose connection | 2021-07-02 | 17:00PM | Vinay
153 | 8886616137 | 1 | Bandra | West | Closed | EMS System Need to change | EMS | 272629489 | 2021-07-02 | 7:00 | July | NA | mtrl qte sent on 05/07 apprvd,lbr on06/7 | 2021-03-08 | 18:00 PM | Vinay | b
154 | 2019000094 | 355 | Bangaluru-Kadubesnahali-Presti | South | Closed | Ems data not coming prperly | EMS | 293330738 | 2021-07-14 | 15:30 PM | July | NA | GSM Anteena Problem Qte sent waiting for Po | closed |  | --- | b
155 | 9666087937 | 172 | Arcot Road | South | Closed | Temperature sensor installation | EMS | 286322125 | 2021-07-16 | 18:30 PM | July | NA | Temperature installation completed | 30-07-21 | 14:00 PM | Rangesh Sir | b
156 | 2018000075 | 181 | Sai Elegnace | West | closed | Relay Mother board not working | EMS | 246897214 | 2021-07-24 | 10:30 | July | NA | Relay Mother board servicing Done | 24-09-21 | 15:00 PM | Vinay | Billing
157 | 2020000039 | 376 | Mumbai T2 Terminal Airport | West | open | Ems Not working | EMS | 246861338 | 2021-08-03 | 7:00 | Aug | NA | Need to visit |  |  | Vinay
157 | 7997993011 | 140 | Signature Mall | South | Closed | Ems Not working | EMS | 299344120 | 2021-08-05 | 23:48 Pm | Aug | NA | Sim Card issue , replaced new one. | 2021-08-06 | 13:00 PM | Madhu |  | FSR recieved
158 | 9666090253 | 134 | HYD-0134-Tolychowki | West | Closed | Ems Not working | EMS | 296311731 | 2021-07-27 | 11:30 | July | NA | Signal booster installed | 2021-10-08 | 13:00PM | Anil |  | FSR Recieved
159 | 9666092371 | 87 | Khedshivapur | West | open | Dg EMS wire is broken and reading not seen | EMS | 298690525 | 2021-08-05 | 10.30 AM | Aug | NA | Need to visit |  |  | Nitin
160 | 2018000096 | 333 | Wagoli | West | open | DG Filling reading not showing | EMS | 299797468 | 2021-08-08 | 10.30 AM | Aug | NA | Need to visit |  |  | Nitin
161 | 9666101726 | 166 | JLB Road Mysore | South | open | DG fuel data not showing | EMS | 287505425 | 2021-08-09 | 14.30 PM | Aug | NA | Need to visit |  |  | Madhu | Billing
162 | 7997993021 | 20 | Ghatkopar | West | Closed | Ems Not working | EMS | 283467124 | 2021-08-05 | 14:30 PM | Aug | NA | GSM Modem problem | 2021-11-08 | 6:00 | Bala koteshwar |  | FSR Recieved
163 | 2017000056 | 67 | Channapatna | West | Closed | DG readings kwh not showing Correct | EMS | 299290182 | 2021-08-06 | 22:03 PM | Aug | NA | Bulk in board, mother board changed now readings are showing | 2021-08-16 | 16:00 Pm | Madhu |  | FSR recieved
164 | 9133382082 | 180 | Koramangala | South | Closed | Misc Showing high | EMS | 299951263 | 2021-08-08 | 17:30 PM | Aug | NA | Connection are interchange with all meters | 13-08-21 | 16:00 PM | Madhu |  | FSR recieved
164 | 9676110586 | 105 | Himayathnagar | South | Closed | Kitchen data not picking up | EMS | 300666637 | 2021-08-13 | 18:00 PM | Aug | NA | CT Ratio Changed | 30-08-21 | 15:00 PM | Anil
165 | 7729986541 | 165 | Sis Mall | South | Closed | Hvac auto controll not happennign | EMS | 301085672 | 2021-08-16 | 9:45 | Aug | NA | Hvac auto control connection done | 15-09-21 | 16:30 PM | Anil |  | FSR recieved
166 | 2019000083 | 332 | GSM Mall Miyapur | South | Closed | Kitchen meter data not getting properly which is Ct changed recently | EMS | 301085875 | 2021-08-16 | 9:45 | Aug | NA | checked R and y phase load not showing need to replace new Ct's | closed (30/8/21) |  | Anil |  | FSR recieved
167 | 7997993048 | 242 | Sonali | West | Closed | Gas & Munter readings not showing | EMS | 300377823 | 2021-08-11 | 19:00 PM | Aug | NA | Fuse Board changed | 27-08-21 | 14:00PM | Nitin |  | FSR recieved
168 | 2017000054 | 209 | JP Nagar | South | Closed | Ems not working | EMS | 300475361 | 2021-08-14 | 16:00 PM | Aug | NA | Internally Looping connection changed | 22/08/2021 | 14:00 PM | Madhu |  | FSR recieved
169 | 7658937700 | 104 | Jayanagar | South | Closed | Ems proper readings not showing | EMS | 300521487 | 2021-08-14 | 20:30 PM | Aug | NA | Internally Looping connection changed | 23/08/2021 | 16:00PM | Madhu |  | FSR recieved
170 | 2017000058 | 100 | Baseshwara Nagar | South | Closed | Ems HVAC meter not working | EMS | 300706243 | 2021-08-15 | 21:30 PM | Aug | NA | New Energy meter installed | 2021-04-09 | 6:00 | Madhu | billing
171 | 2018000088 | 326 | Pune-Kharadi-Ganga Platino-Pune | West | Closed | DG Reading not showing | EMS | 300860097 | 2021-08-05 | 10.30 AM | Aug | NA | Not possible to install |  |  | Nitin
172 | 2017000001 | 114 | Shoolagiri | South | open | EMS Reading error | EMS | 301265899 | 2021-08-17 | 12:51 | Aug | NA | Quote sent waiting for approvel |  |  | Madhu
173 | 9666089162 | 90 | Grand Arcade | South | Closed | Gas Flow meter Calibaration | EMS | 300083099 | 2021-08-17 | 17:00 PM | Aug | NA | Calibaration done | 28-08-21 | 14:00 PM | Rangesh Sir
174 | 2017000063 | 286 | Chennai Nazrathpeth | South | Closed | Gas Flow meter Calibaration | EMS | 300083100 | 2021-08-17 | 17:00 PM | Aug | NA | Need to visit | 27-08-21 | 13:00 PM | Rangesh Sir
175 | 2019000111 | 350 | Chennai-Omr-Gire | South | Closed | Gas Flow meter Calibaration | EMS | 300647447 | 2021-08-17 | 17:00 PM | Aug | NA | Gas meter calibaration done | 27-08-21 | 16:00 PM | Rangesh Sir
176 | 2018000063 | 321 | MPM Mall | South | Closed | Gas meter consumption not matching | EMS | 301437551 | 2021-08-18 | 21:00 PM | Aug | NA | visited and gasflow meter calibration done | 24-08-21 | 14:00PM | Anil |  | Issued Cleared in load meter installation
177 | 7997993037 | 206 | Gaganpahad | South | Closed | Gas meter consumption not matching | EMS | 301437404 | 2021-08-18 | 21:00 PM | Aug | NA | visited and gasflow meter calibration dine | 26-08-21 | 17:00Pm | Anil |  | Issued Cleared in load meter installation
178 | 2018000053 | 322 | Jublihills | South | Closed | Kitchen and HVAC meter not showing Proper data. | EMS | 301439390 | 2021-08-18 | 21:00 PM | Aug | NA | visited and kitchen and hvac meter ct ratio checked and changed |  |  | Anil |  | FSR recieved
179 | 9666091356 | 39 | Brigade | South | open | EB Main Meter going negative | EMS | 301515838 | 2021-08-18 | 19:00PM | Aug | NA | Need to visit |  |  | Madhu
180 | 9666101791 | 66 | Kasturba Road | South | Closed | Misc Showing high | EMS | 301516585 | 2021-08-18 | 19:00PM | Aug | NA | Need to visit |  |  | Madhu |  | FSR Not required
181 | 7729986534 | 96 | Commercial Street | South | Closed | Misc Showing high | EMS | 301517200 | 2021-08-18 | 19:00PM | Aug | NA | Need to visit |  |  | Madhu |  | FSR Not required
182 | 2017000052 | 147 | Orian Mall | South | Closed | Misc Showing high | EMS | 301534667 | 2021-08-18 | 19:00PM | Aug | NA | Need to visit |  |  | Madhu |  | FSR Not required
183 | 7997993017 | 95 | Lido Mall | South | Closed | Ems reading high | EMS | 301535338 | 2021-08-18 | 19:00PM | Aug | NA | Need to visit |  |  | Madhu |  | FSR Not required
184 | 9666090861 | 85 | Bel Road | South | Closed | Ems reading high | EMS | 301535785 | 2021-08-18 | 19:00PM | Aug | NA | Kitchen Energy meter CT coils and meter changed | 2021-06-09 | 11:00 | Madhu |  | FSR recieved
185 | 7997993024 | 2 | Lokhandwala Complex | West | Closed | EMS Economizer Reading not showing | EMS | 301743890 | 2021-08-20 | 1:37 | Aug | NA | Loose connection in module | 23-08-21 | 23:00 PM | Suresh |  | FSR recieved
186 | 2019000121 | 343 | MUMBAI-BORIVLI-DONBOSCO | West | Closed | EMS Economizer Reading not showing | EMS | 301744047 | 2021-08-20 | 1:37 | Aug | NA | Munter CT replace,installation completed | 2021-04-10 | 12:45 | Vinay
187 | 9951945925 | 265 | MUMBAI NAIGON MALJIPADA | West | Closed | EMS Economizer Reading not showing | EMS | 301744466 | 2021-08-20 | 1:37 | Aug | NA | Communication cable Loose connection | 28-08-21 | 23:00 PM | Vinay
188 | 2017000055 | 117 | Minakshi Mall | South | Closed | Misc Showing high | EMS | 300813805 | 2021-08-16 | 12:37 | Aug | NA | Internally Looping connection changed | 17-08-21 | 14:00 PM | Madhu |  | FSR recieved
188 | 7997993011 | 140 | Signature Mall | South | Closed | EMS data not getting | EMS | 299344120 | 2021-08-24 | 10:00 | Aug | NA | Need to visit |  |  | Madhu |  | FSR recieved
189 | 2018000023 | 315 | Kadugodi | South | open | Gas meter issue | EMS | 301119280 | 2021-08-20 | 10:00 | Aug | NA | Need to visit |  |  | Madhu
190 | 2017000010 | 108 | Pegasus Prahladnagar | West | Closed | EMS Not Working | EMS | 301119280 | 2021-08-20 | 10:00 | Aug | NA | Communication cable changed | 2021-08-09 | 14:00 PM | Vinay
191 | 2019000046 | 349 | Gandhi Nagar | West | Closed | Relay box is mising | EMS | 301446840 | 2021-08-26 | 11.20.00 | Aug | NA | Material missing from store end |  |  | ---
192 | 7658940002 | 199 | Kalawad Road Rajkot | West | Closed | Data is not coming Correct | EMS | 301981111 | 2021-08-26 | 14:00 PM | Aug | NA | CT Ratio Changed | 2021-07-09 | 10:00 | Vinay
193 | 2017000010 | 108 | Pegasus Prahladnagar | West | Closed | EMS Relay box not getting any Command and Network issue | EMS | 301969510 | 2021-08-26 | 14:00 PM | Aug | NA | Gate way Locatin changed | 2021-08-09 | 14:00 PM | Vinay
194 | 9666098603 | 92 | Peenya | South | Closed | Hvac meter data not getting | EMS | 302820605 | 2021-08-26 | 16:20 PM | Aug | NA | Internall connection inter changed | 29-08-21 | 17:00 PM | Madhu
195 | 7997993046 | 214 | Simhagad Road | West | Closed | HVAC KWH meter not showing reading | EMS | 302255076 | 2021-09-01 | 12.00 PM | Sep | NA | New energy meter installed | 2021-04-09 | 16:00 PM | Nitin | Billing | FSR Submitted
196 | 2018000073 | 3 | Vashi Sector 13 | West | Closed | Ems not working | EMS | 305811324 | 2021-09-16 | 14.00 PM | Sep | NA | Gsm Modem replaced | 17-09-21 | 17:00 Pm | vinay
197 | 9666092148 | 120 | PUN-0120-PAUD Road | West | open | Hvac meter not working | EMS | 304920411 | 2021-09-06 | 23:33 PM | Sep | NA | Need to visit |  |  | Nitin
198 | 2018000085 | 325 | Kakinada Mall | South | open | Ems energy meter issue | EMS | 306398142 | 2021-09-14 | 17:39 PM | Sep | NA | Need to visit |  |  | Madhu
199 | 9951945297 | 271 | Vijayawada | South | open | Ems energy meter issue | EMS | 306399551 | 2021-09-14 | 17:39 PM | Sep | NA | Need to visit |  |  | Madhu
200 | 7997993023 | 7 | Cross Road | West | open | Energy Meter need to install | EMS | 308691270 | 2021-09-23 | 12:00 | Sep | NA | Quote sent waiting for approvel |  |  | vinay
201 | 7997993019 | 18 | Metro House | West | Closed | EMS data not getting | EMS | 310149621 | 2021-09-27 | 17:59 PM | Sep | NA | Gsm Modem Replaced | 29-09-21 | 14:00 PM | vinay
202 | 9951945297 | 248 | Palghar Manor NH8 | West | open | EMS DG Reading not showing | EMS | 311096913 | 2021-09-30 | 13:00 PM | Sep | NA | Quote sent waiting for approvel |  |  | vinay
Note on N127: no response fm mcdee so closed through mail 21/07
Note on N128: he said by monday he would revrt
Note on N129: he said by monday he would revrt
Note on N140: complaint cosed via mail by protech21/07 accptd by sachin ptil
Note on N146: new MTR quote sent on 20/07

## PROJECT (SURVEY & INSTALLATION)
Sl No | Store Code | StationName | Region | Status demo or bill | protec Ser engg name | Nature of instln | Equipment Description | Log Time | date | Priority | Feedback | Job compltd Date | Closing Time | Instln/srvic rport date | Insln sent sft cpy to prbhu date | Dt of submison of hard copy to a/c | Final closer dt after submisn of hrd cpy | Inv generated dt | Pod to custmr | Soft copy to custmr dt | Payment rcpt dt
1 |  | focus mall,calicut | south | B | Thomos | [5 empty] | installed ,data receiving | 23 /07/2021 |  |  | 2021-04-08
2 |  | Gmr, Hyderabad | south | B | Anil | [5 empty] | installed ,data receiving | 2021-03-08 | 17:00 PM | 2021-04-08
3 |  | Chotabhai, Chennai | south | B | Rangesh sir | [5 empty] | installed ,data receiving | 21/08/2021 | 16:00 PM |  | 22/08/2021
4 |  | GNP Galaxy Ambernath | West | B | Vinay/Suresh | [5 empty] | installed ,data receiving | 16/09/2021 | 16:00 PM
5 |  | Chikkajala Hoboli | south | B | Madhu | [5 empty] | installed ,data receiving | 16/09/2021 | 16:00 PM
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on L4: all work done on 14/07 except gas on23/7 gas is ok

## DALY COMPLNT (phone only)
Sl No | Status | Complaint Type | Store Code | Store Name | Associate | Equipment's | FA Code | Comp No.# | Complaint Details | Log Date | Time | Month | Vendor | Patch | Close Date | Close Time | Spares | Service | Total | Categeory | Reason/ Root Cause | Action | Aging Days | Hrs | TAT
113 |  |  | 2017000066 | 306 | Manipal | South | open | EMS Kitchen and HVAC data not coming | EMS | M11504 | 2021-01-30 | 13:40 PM | Jan | NA | Need to visit
114 |  |  | 2018000015 | 225 | ForumFizaMall Mangalore | South | open | EMS data miscellaneous units showing high need | EMS | M11963 | 2021-02-11 | 11:40 | Feb | NA | Need to visit
115 |  |  | 9666098645 | 184 | DownTown Park | South | Closed | EMS data miscellaneous units showing high need to resolve . | EMS | M11964 | 2021-02-11 | 11:40 | Feb | NA | CT Coils Installed for HVAC | 2021-02-19
125 |  |  | 7997993035 | 138 | Hitech city | South | open | Gas Reading not getting proper | EMS | 247999143 | 2021-05-07 | 10:00 | May | NA | 01/07,prabhu+ravi had a concall with prasd karri
126 |  |  | 7997993037 | 206 | Gaganpahad | South | open | Gas Reading not getting proper | EMS | 247997195 | 2021-05-07 | 10:00 | May | NA | 01/07,prabhu+ravi had a concall with prasd karri
127 |  |  | 7997993039 | 240 | AppajiNagar | South | open | Gas Reading not getting proper | EMS | 248003245 | 2021-05-07 | 10:00 | May | NA | 01/07,prabhu+ravi had a concall with prasd karri
133 |  |  | 9666093184 | 43 | P C M C | West | Closed | Ems control Gas flow meter not working | EMS | 255548741 | 2021-06-05 | 21:30 | June | NA | New Gas flow meter dispatched | 30-06-2021
134 |  |  | 2018000088 | 326 | Pune-Kharadi | West | open | Gas Flow meter not working | EMS | 268984184 | 2021-06-05 | 8.00 PM | June | NA | New Gas flow meter dispatched
1 | Closed | Controller Issue | 298 | CMR Vizag | Zakir | EMS | --- | --- | Timings issue | 2021-08-07 | 14:00 PM | July | Protech | NA | 2021-08-07 | 15:00 PM | --- | Done |  |  | Timings Extended | Immediate | 0 | 30 Minutes | 0
2 | Closed | Controller Issue | 252 | Rohit DT mall | Ajith | EMS | --- | --- | Timings issue | 2021-11-07 | 21:30 PM | July | Protech | NA | 2021-11-07 | 21:45PM | --- | Done |  |  | Timings Extended | Immediate | 0 | 15 Minutes | 0
3 | Closed | Controller Issue | 91 | Inorbit Mall | Prasad Karri | EMS | --- | --- | Singage Getting off automatically | 2021-12-07 | 15:36 PM | July | Protech | NA | 2021-12-07 | 16:00 PM | --- | Done |  |  | Singage Timings issue,timings changed | Immediate | 0 | 15 Minutes | 0
4 | Closed | Controller Issue | 340 | Sarathcity LG-4 Floor | Prasad Karri | EMS | --- | --- | Vatts are not getting On | 15-07-21 | 12:36 | July | Protech | NA | 15-07-21 | 13:00 PM | --- | Done |  |  | Issue from Store End | Immediate | 0 | 15 Minutes | 0
5 | Closed | Controller Issue | 163 | Koperkhairani | Sachin Patel | EMS | --- | --- | Vatts are not getting On | 17-07-21 | 10:36 | July | Protech | NA | 17-07-21 | 10:45 | --- | Done |  |  | Mcb Trip from store end | Immediate | 0 | 15 Minutes | 0
6 | Closed | Controller Issue | 145 | CBD Belapur | Ajith | EMS | --- | --- | Vatts are off Suddenly | 22-07-21 | 14:36 PM | July | Protech | NA | 22-07-21 | 14:42 PM | --- | Done |  |  | Loose connection near switch controlller box | Immediate | 0 | 07 Minutes | 0
7 | Closed | Controller Issue | 213 | Rebale | Ajith | EMS | --- | --- | Vatts are off Suddenly | 2021-05-08 | 10:30 | Aug | Protech | NA | 2021-05-08 | 11:00 | --- | Done |  |  | Relay not working | Immediate | 0 | 15 Minutes | 0
8 | Closed | Controller Issue | 51 | Eco Space | Yogesh | EMS | --- | --- | Vatts are not getting On | 2021-10-08 | 11:25 | Aug | Protech | NA | 2021-10-08 | 11:30 | --- | Done |  |  | Timings issue | Immediate | 0 | 5 Minutes | 0
9 | Closed | Controller Issue | 272 | Nameshree | Prasad Karri | EMS | --- | --- | Kitchen exhaust not getting On | 17-08-21 | 11:20 | Aug | Protech | NA | 17-08-21 | 11:40 | --- | Done |  |  | Main Panel Mcb trip from store end | Immediate | 0 | 10 minutes | 0
10 | Closed | Controller Issue | 167 | LuLu Mall | Zakir | EMS | --- | --- | Kitchen exhaust not getting On | 17-09-21 | 11:20 | Sep | Protech | NA | 17-09-21 | 11:40 | --- | Done |  |  | Timings issue | Immediate | 0 | 20 minutes | 0
11 | Closed | Controller Issue | 134 | Tolichowki | Prasad Karri | EMS | --- | --- | Singage Not getting On | 20-09-21 | 17:20 PM | Sep | Protech | NA | 20-09-21 | 17:20 PM | --- | Done |  |  | Timings issue | Immediate | 0 | 10 minutes | 0
12 | Closed | Controller Issue | 31 | Kothrud | Santosh Nikam | EMS | --- | --- | Kitchen exhaust not getting On | 17-09-21 | 11:20 | Sep | Protech | NA | 17-09-21 | 11:40 | --- | Done |  |  | Timings Extended | Immediate | 0 | 20 minutes | 0
13 | Closed | Controller Issue | 240 | Appaji Nagar | Prasad Karri | EMS | --- | --- | Kitchen exhaust not getting On | 23-09-21 | 20:10 PM | Sep | Protech | NA | 23-09-21 | 20:10 PM | --- | Done |  |  | Timings Changed | Immediate | 0 | 10 minutes | 0
Note on P5: he said by monday he would revrt
Note on P6: he said by monday he would revrt
Note on P7: he said by monday he would revrt