## Sheet1
Sl No | Code | Store Name | Switch Control Module | cost of sw cntrl | cost of instln sw cntrl | HVAC DX Module | Cost of dx mdl | cost of instln of dx | Wire to wireless | cost of wireles | cost of instln wireless | Installation Status | basic cost of sw cntrl | basic cost of dx mdl | basic cost of wireless | basic cost of instln sw | basic cost of instln hvac | basic cost of instln wireless | GST 18 % | TOTAL COST WITH GST | Actual HVAC | Actual Switch Control Module
1 | 1 | Bandra | - | 9750 | 1000 | 5 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 49250 | 0 | 0 | 7500 | 0 | 10215 | 66965 | 5 | -
2 | 2 | Lokhandwala | - | 9750 | 1000 | 4 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 39400 | 0 | 0 | 6000 | 0 | 8172 | 53572 | 4 | -
3 | 3 | Vashi Sector-17 | 3 | 9750 | 1000 | 2 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 19700 | 9650 | 3000 | 3000 | 1500 | 11898 | 77998 | 2 | 3
4 | 4 | Vile Parle | - | 9750 | 1000 | 7 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 68950 | 0 | 0 | 10500 | 0 | 14301 | 93751 | 7 | -
5 | 6 | New Empire | 3 | 9750 | 1000 | 2 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 19700 | 9650 | 3000 | 3000 | 1500 | 11898 | 77998 | 2 | 3
6 | 7 | Crossroads | - | 9750 | 1000 | 2 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 0 | 19700 | 9650 | 0 | 3000 | 1500 | 6093 | 39943 | 2 | -
7 | 10 | Thane | 2 | 9750 | 1000 | 6 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 19500 | 59100 | 9650 | 2000 | 9000 | 1500 | 18135 | 118885 | 6 | 2
8 | 12 | Kalamboli | - | 9750 | 1000 | 8 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 78800 | 0 | 0 | 12000 | 0 | 16344 | 107144 | 8 | -
9 | 15 | Phoenix Mills | - | 9750 | 1000 | 2 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 19700 | 0 | 0 | 3000 | 0 | 4086 | 26786 | 2 | -
10 | 17 | Mulund | 2 | 9750 | 1000 | 3 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 19500 | 29550 | 9650 | 2000 | 4500 | 1500 | 12006 | 78706 | 3 | 2
11 | 18 | Colaba | - | 9750 | 1000 | 2 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 19700 | 0 | 0 | 3000 | 0 | 4086 | 26786 | 2 | -
12 | 20 | Ghatkopar | 2 | 9750 | 1000 | 4 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 19500 | 39400 | 9650 | 2000 | 6000 | 1500 | 14049 | 92099 | 4 | 2
13 | 22 | Borivili | - | 9750 | 1000 | 3 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 29550 | 0 | 0 | 4500 | 0 | 6129 | 40179 | 3 | -
14 | 25 | The Hub | - | 9750 | 1000 | 2 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 19700 | 0 | 0 | 3000 | 0 | 4086 | 26786 | 2 | -
15 | 46 | Mumbai Central Ii-Patel | - | 9750 | 1000 | 2 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 0 | 19700 | 9650 | 0 | 3000 | 1500 | 6093 | 39943 | 2 | -
16 | 50 | Thakur Mall-Dahisar | 3 | 9750 | 1000 | 6 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 59100 | 9650 | 3000 | 9000 | 1500 | 20070 | 131570 | 6 | need to confirm from vinay
17 | 56 | Mumbai- Metro Junction | 3 | 9750 | 1000 | 2 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 19700 | 9650 | 3000 | 3000 | 1500 | 11898 | 77998 | 2 | 3
18 | 70 | Kharghar- Little World | - | 9750 | 1000 | 4 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 39400 | 0 | 0 | 6000 | 0 | 8172 | 53572 | 4 | -
19 | 79 | Mumbai- Mira Bhayandar | 3 | 9750 | 1000 | 6 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 59100 | 9650 | 3000 | 9000 | 1500 | 20070 | 131570 | 6 | 3
20 | 107 | Mumbai-Dahisar Link Rd | - | 9750 | 1000 | 5 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 49250 | 0 | 0 | 7500 | 0 | 10215 | 66965 | 5 | -
21 | 109 | Shivai-Andheri Kurla Rd | 2 | 9750 | 1000 | 2 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 19500 | 19700 | 9650 | 2000 | 3000 | 1500 | 9963 | 65313 | 2 | 2
22 | 135 | Mumbai-Cafe Ideal Andheri | 2 | 9750 | 1000 | 2 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 19500 | 19700 | 9650 | 2000 | 3000 | 1500 | 9963 | 65313 | 2 | 2
23 | 145 | Mumbai-Sai Sagar Belapur | 3 | 9750 | 1000 | 3 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 29550 | 9650 | 3000 | 4500 | 1500 | 13941 | 91391 | 3 | 3
24 | 149 | Mumbai-Star Mall | - | 9750 | 1000 | 3 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 29550 | 0 | 0 | 4500 | 0 | 6129 | 40179 | 3 | -
25 | 151 | Mumbai-Lodha Boulevard | - | 9750 | 1000 | 3 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 29550 | 0 | 0 | 4500 | 0 | 6129 | 40179 | 3 | -
26 | 161 | Mumbai-Vishwamahal Mulund | 3 | 9750 | 1000 | 11 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 108350 | 9650 | 3000 | 16500 | 1500 | 30285 | 198535 | 11 | 3
27 | 163 | Mumbai-Koparkhairane | - | 9750 | 1000 | 3 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 29550 | 0 | 0 | 4500 | 0 | 6129 | 40179 | 3 | -
28 | 171 | Ripples - Navi Mumbai | - | 9750 | 1000 | 5 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 49250 | 0 | 0 | 7500 | 0 | 10215 | 66965 | 5 | -
29 | 181 | Mumbai Sai Elegance | - | 9750 | 1000 | 6 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 59100 | 0 | 0 | 9000 | 0 | 12258 | 80358 | 6 | -
30 | 193 | Kalyan Shelar Park | - | 9750 | 1000 | 5 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 0 | 49250 | 9650 | 0 | 7500 | 1500 | 12222 | 80122 | 5 | -
31 | 205 | Mumbai Landmark Bhayander | - | 9750 | 1000 | 3 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 29550 | 0 | 0 | 4500 | 0 | 6129 | 40179 | 3 | -
32 | 212 | Mumbai A To Z Vasai | 3 | 9750 | 1000 | 2 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 29250 | 19700 | 0 | 3000 | 3000 | 0 | 9891 | 64841 | 2 | 3
33 | 213 | Mumbai Rabale | 3 | 9750 | 1000 | 2 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 19700 | 9650 | 3000 | 3000 | 1500 | 11898 | 77998 | 2 | 3
34 | 215 | Mumbai Nts Bandra | 2 | 9750 | 1000 | 6 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 19500 | 59100 | 9650 | 2000 | 9000 | 1500 | 18135 | 118885 | 6 | 2
35 | 222 | Mumbai Andheri Vaibhav | - | 9750 | 1000 | 4 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 39400 | 0 | 0 | 6000 | 0 | 8172 | 53572 | 4 | -
36 | 227 | Mumbai Anupam Goregaon | 3 | 9750 | 1000 | 4 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 39400 | 9650 | 3000 | 6000 | 1500 | 15984 | 104784 | 4 | 2
37 | 238 | Mumbai Shalimar | 3 | 9750 | 1000 | 4 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 29250 | 39400 | 0 | 3000 | 6000 | 0 | 13977 | 91627 | 4 | 3
38 | 251 | Panvel Balaji Aangan | 3 | 9750 | 1000 | 6 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 59100 | 9650 | 3000 | 9000 | 1500 | 20070 | 131570 | 6 | 3
39 | 252 | Walshind Mumbai Nashik Hi | 3 | 9750 | 1000 | 5 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 49250 | 9650 | 3000 | 7500 | 1500 | 18027 | 118177 | 5 | 3
40 | 265 | Mumbai Naigon Maljipada | 3 | 9750 | 1000 | 5 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 49250 | 9650 | 3000 | 7500 | 1500 | 18027 | 118177 | 5 | 3
41 | 275 | Mumbai Jogeshwari Jaiswal | 3 | 9750 | 1000 | 4 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 39400 | 9650 | 3000 | 6000 | 1500 | 15984 | 104784 | 4 | 3
42 | 284 | Kharghar Pacific Heights | 2 | 9750 | 1000 | 2 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 19500 | 19700 | 9650 | 2000 | 3000 | 1500 | 9963 | 65313 | 2 | 2
43 | 285 | Mumbai Sion Avishkar | 3 | 9750 | 1000 | 4 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 39400 | 9650 | 3000 | 6000 | 1500 | 15984 | 104784 | 4 | 3
44 | 294 | Mumbai Vile Parle Nivara | 2 | 9750 | 1000 | 7 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 19500 | 68950 | 9650 | 2000 | 10500 | 1500 | 20178 | 132278 | 6 | 2
45 | 299 | Mumbai Artista | 3 | 9750 | 1000 | 5 | 9850 | 1500 | 1 | 9650 | 1500 | Installation Done | 29250 | 49250 | 9650 | 3000 | 7500 | 1500 | 18027 | 118177 | 5 | 3
46 | 305 | Mumbai Bhandup Magnet Mal | - | 9750 | 1000 | 2 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 19700 | 0 | 0 | 3000 | 0 | 4086 | 26786 | 2 | -
47 | 319 | Dombivili Gharda Circle | - | 9750 | 1000 | 3 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 0 | 29550 | 0 | 0 | 4500 | 0 | 6129 | 40179 | 3 | -
48 | 344 | Mumbai Thane Ghodbunder | 3 | 9750 | 1000 | 2 | 9850 | 1500 | - | 9650 | 1500 | Installation Done | 29250 | 19700 | 0 | 3000 | 3000 | 0 | 9891 | 64841 | 2 | 3
3654165